## 项目进度
|  | 3月 | [13 empty] | 4月
|  | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1.1 | 项目文档模板 | [44 empty] | 计划 | bar: 3月 18 to 3月 20
1.2 | 项目计划编制 | [44 empty] | 进行中 | bar: 3月 19
1.3 | 沟通计划编制 | [44 empty] | 已完成 | bar: 3月 18
1.4 | 测试计划编制 | [44 empty] | 里程碑 | bar: 3月 19 to 3月 20
M1 | 客户sign off 项目计划 | bar: 3月 21
2.1 | 需求调查 | bar: 3月 21 to 3月 22
2.2 | 需求分析 | bar: 3月 23 to 3月 25
M2 | 提交文档目录 | bar: 3月 24
2.3 | 编写需求文档 | bar: 3月 26 to 3月 29
3.1 | 系统架构设计 | bar: 3月 26 to 3月 29
3.2 | 数据建模设计 | bar: 3月 30 to 3月 30
3.3 | 系统原型设计 | bar: 4月 1 to 4月 4
3.4 | 移动系统原型设计 | bar: 4月 1 to 4月 3
3.5 | 系统UI设计 | bar: 3月 20 to 3月 21
M3 | 提交需求和系统架构文档 | bar: 4月 2
3.6 | 用户管理模块详细设计 | bar: 4月 5 to 4月 7
3.7 | 菜品浏览模块详细设计 | bar: 4月 5 to 4月 7
3.8 | 点菜下单模块详细设计 | bar: 4月 5 to 4月 7
3.9 | 模块4详细设计
3.10 | 模块5详细设计
3.11 | 模块6详细设计
3.12 | 模块7详细设计
3.13 | 模块8详细设计
4.1 | 测试策略编制 | bar: 3月 26 to 3月 27
4.2 | 用户管理模块测试用例 | bar: 3月 30 to 4月 1
4.3 | 菜品浏览模块测试用例 | bar: 4月 2 to 4月 3
4.4 | 点菜下单模块测试用例 | bar: 4月 4 to 4月 6
M4 | 提交详细设计和测试文档 | bar: 4月 8
4.5 | 模块4测试用例
4.6 | 模块5测试用例
4.7 | 模块6测试用例
4.8 | 模块7测试用例
4.9 | 模块8测试用例
5.1 | 用户管理模块实现 | bar: 4月 8 to 4月 10
5.2 | 菜品浏览模块实现 | bar: 4月 8 to 4月 10
5.3 | 点菜下单模块实现 | bar: 4月 11 to 4月 13
5.4 | 模块4实现
5.5 | 模块5实现
5.6 | 模块6实现
5.7 | 模块7实现
5.8 | 模块8实现
6.1 | 系统集成测试(一阶段) | bar: 4月 14 to 4月 15
6.2 | 项目交付物打包(一阶段) | bar: 4月 16
M5 | 一阶段交付 | bar: 4月 16
6.3 | 系统集成测试(二阶段)
6.4 | 测试报告
6.5 | 用户验收测试
6.6 | 项目交付物打包（二阶段）
Note on C3: Author: Annie
Note on D4: Author: Aaron
Note on C5: Author: Lin
Note on E6: Author: Annie
Note on F7: Author: Aaron
Note on G8: Author: All
Note on H9: Author: All
Note on K11: Author: Aaron/Annie/Leon
Note on N12: Author: Lin/Aaron/Leon
Note on O13: Author: Lin/Aaron/Leon
Note on P13: Author: Lin/Aaron/Leon
Note on T14: Author: Lin/Aaron
Note on S15: Author: Leon
Note on W18: Author: Lin
Note on W19: Author: Aaron
Note on W20: Author: Leon
Note on L26: Author: Annie
Note on Q27: Author: Annie
Note on S28: Author: Annie
Note on U29: Author: Annie

## 项目进度(二期)
任务分解WBS |  | 工时(人时） | 5月 | [22 empty] | 6月 | [29 empty] | 7月
 | time axis 2014-03-09 to 2014-05-11
7.1 | Hibernate架构重构 | 8 | [64 empty] | 计划 | bar: 2014-03-09 to 2014-03-10
7.2 | 代码结构重构 | 4 | [64 empty] | 进行中 | bar: 2014-03-11
7.3 | Tiles模板 | 28 | [64 empty] | 已完成 | bar: 2014-03-12 to 2014-03-15
7.4 | 新UI | 56 | [64 empty] | 里程碑 | bar: 2014-03-16 to 2014-03-25
M1 | 新UI移植+用户管理功能移植 | bar: 2014-03-25
7.5 | 文档更新 | 4 | bar: 2014-03-09
3.7 | 移动点菜-下单功能详细设计 | 4 | bar: 2014-03-10
4.3 | 移动点菜-下单功能测试用例 | 4 | bar: 2014-03-10
5.2 | 移动点菜-下单功能模块实现(WS) | 12 | bar: 2014-03-11 to 2014-03-12
5.2 | 移动点菜-下单功能模块实现(Android) | 12 | bar: 2014-03-13 to 2014-03-15
3.7 | 移动点菜-历史订单详细设计 | 4 | bar: 2014-03-16
4.3 | 移动点菜-历史订单测试用例 | 4 | bar: 2014-03-16
5.2 | 移动点菜-历史订单模块实现(WS) | 12 | bar: 2014-03-17 to 2014-03-19
5.2 | 移动点菜-历史订单模块实现(Android) | 12 | bar: 2014-03-20 to 2014-03-22
3.8 | 菜单管理模块详细设计 | 12 | bar: 2014-03-13 to 2014-03-15
4.4 | 菜单管理模块测试用例 | 12 | bar: 2014-03-16 to 2014-03-18
5.3 | 菜单管理模块实现 | 112 | bar: 2014-03-16 to 2014-03-22; 2014-03-26 to 2014-04-03
M2 | 移动端+ws交付 | bar: 2014-03-30
3.9 | 收银管理模块详细设计 | 8 | bar: 2014-04-04 to 2014-04-05
4.5 | 收银管理模块测试用例 | 8 | bar: 2014-04-04 to 2014-04-05
5.4 | 收银管理模块实现 | 64 | bar: 2014-04-06 to 2014-04-15
3.10 | 会员管理模块详细设计 | 8 | bar: 2014-04-12 to 2014-04-13
4.6 | 会员管理模块测试用例 | 8 | bar: 2014-04-12 to 2014-04-13
5.5 | 会员管理模块实现 | 72 | bar: 2014-04-14 to 2014-04-18
6.3 | 系统集成测试(二阶段) | 16 | bar: 2014-04-19 to 2014-04-22
6.6 | 项目交付物打包(二阶段) | 8 | bar: 2014-04-23 to 2014-04-24
Note on E3: Author: Aaron
Note on F4: Author: Aaron/Lin
Note on K6: Author: Lin
Note on D8: Author: Aaron
Note on E9: Author: Aaron
Note on E10: Author: Annie
Note on G11: Author: Aaron
Note on H12: Author: Leon
Note on K13: Author: Aaron
Note on K14: Author: Annie
Note on N15: Author: Aaron
Note on Q16: Author: Leon
Note on J17: Author: Aaron/Lin
Note on M18: Author: Annie
Note on AA19: Author: Aaron/Lin
Note on AE21: Author: Aaron/Lin
Note on AE22: Author: Annie
Note on AO23: Author: Lin Aaron will quit after 6 days
Note on AM24: Author: Aaron
Note on AM25: Author: Annie